## Web-based
Pump Operations with Mobile App System |  |  | LEGENDS
Working Days (Timeline) |  |  |  |  | - | Not yet Started | [7 empty] | On Resume
[5 empty] | - | Started | [6 empty] | - | For Testing
Date Re-started: May 21, 2020 |  |  |  |  | - | On-going | [6 empty] | - | Done
Estimated Date Finished: July 31, 2020 |  |  |  |  | - | Paused
MAIN MENU | MODULE | SUB-MODULE | May | [10 empty] | June | [29 empty] | July
|  |  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Database Design/modification | bar: May 21 to May 23; May 26 to May 30; June 1 to June 6; June 8 to June 11; June 13; June 16 to June 19
Log-in | bar: May 21
Main Screen (Dashboard) | bar: May 21 to May 23; May 26 to May 30; June 1 to June 6; June 8 to June 11; June 13; June 16 to June 19
User's Account | bar: May 21
Pump Records | Wells | bar: May 21
Control Panel | bar: May 21
Submersible Motor | bar: May 21
Submersible Pump | bar: May 21
Riser Pipe | bar: May 21
Meter Set Assembly | bar: May 21
Chlorinator | bar: May 21
Genset | bar: May 21
Distribution Pressure Points | bar: May 21
Data Entrry | Pump House | bar: May 21
Electrical Consumption | bar: May 21 to May 23; May 26 to May 30; June 1 to June 6; June 8 to June 11
| Pump Lab Test | Bacti Test
P-Chem Test
Pump Non-operational Entries
| Repair and Maintenance | Mainline
Service Connection
Reports | Pump Production
Electrical Consumption History
Bacti-Test History
P-Chem Test History
Repairs and Maintenance
Non-operational Report
Water Balance
| List | Pump House
Wells
Control Panel
Submersible Motor
Submersible Pump
Riser Pipe
Meter Set Assembly
Chlorinator
Genset
Distribution Pressure Points
Water balance Entry | Water Supplies
Authorized Consumption
Water Loses
Admin Settings | Reading Settings
Pump Operators
Users
| Test Analyses | Bacti-Test Analyses
P-Chem Test Analyses
GPM Calculator
Note on H8: Eid al-Fitr 2020
Note on Z8: Independence Day
Note on AC8: Mt. Pinatubo commemoration
Note on AG9: Joko: Not yet final, maybe there will be additional tables and/or fields
Note on D10: Erick: for Validation
Note on AG11: Dashboard Layout - Ok but need to finished all module to adjust page links
Note on X23: Joko: Data Migration Vizcaya Branches

## Notes
Date | Remarks | Personnel
2020-05-30 | Branch Assistance | joko, erick, yumi
2020-06-01 | Branch Assistance | joko, erick, yumi
2020-06-02 | Branch Assistance | joko, erick, yumi
2020-06-03 | Branch Assistance | joko, erick, yumi
2020-06-05 | Data Migration (Vizcaya Branches) | joko
2020-06-06
2020-06-08
2020-06-09
2020-06-10