## Est Timeline
Operations Mobile App
Working Days (Timeline)
Estimated Date Finished: March 31, 2023
MODULE | TARGET USER | SUB-MODULE | DESCRIPTION | STATUS | REMARKS | PROBLEMS ENCOUNTERED | EST. FINISH DATE
PUMP PRODUCTION | PUMP OPERATOR | ON/OFF RECORDS | To capture the total pump operating hours | Done |  | Redesigned - Need to add manual time
|  | FLOW METER READING | To capture the total daily production | Paused | Time Read Overlapping Validation | Redesigned - Need to add manual time | 2023-02-10
|  | PRESSURE READING | To capture the Min, Max and Ave Pump pressure | Paused | Time Read Overlapping Validation | Redesigned - Need to add manual time | 2023-02-10
|  | CHLORINATOR DATA | To capture the chlorine mixture | Done |  | Redesigned - Need to add manual time
|  | PUMP PROBLEMS ENCOUNTERED | To record any pump house realated pronblem encountered | Done |  | Redesigned - Need to add manual time
JOB ORDERS | PLUMBER | SERVICE APPLICATION SURVEY | JO Accomplishments from Elite / To capture water losses | Paused | Redesign and Debug Pump Production Module |  | 2023-02-18
|  | NEW CONNECTION |  | Paused | Redesign and Debug Pump Production Module |  | 2023-02-20
|  | METERING CONCERNS |  | Paused |  |  | 2023-02-21
|  | CHANGE METER |  | Paused |  |  | 2023-02-22
|  | DISCONNECTION - DELINQUENT ACCOUNT |  | Paused |  |  | 2023-02-23
|  | DISCONNECTION - CUSTOMER REQUEST |  | Paused |  |  | 2023-02-24
|  | RECONNECTION |  | Paused |  |  | 2023-02-25
|  | SERVICE LEVEL |  | Paused |  |  | 2023-02-27
|  | ILLEGAL CONNECTION |  | Paused |  |  | 2023-02-28
|  | OTHERS |  | Paused |  |  | 2023-03-01
PUMP REPAIRS AND MAINTENANCE | PUMP OPERATOR | PUMP & MOTOR | Pump Repairs record per Area (JO based) | Not Yet Started |  |  | 2023-03-04
|  | CONTROL PANEL |  | Not Yet Started |  |  | 2023-03-06
|  | PANEL BOARD |  | Not Yet Started |  |  | 2023-03-07
|  | VFD |  | Not Yet Started |  |  | 2023-03-08
|  | METER SET ASSEMBLY |  | Not Yet Started |  |  | 2023-03-09
|  | FLOW METER |  | Not Yet Started |  |  | 2023-03-10
|  | PRESSURE GAUGE |  | Not Yet Started |  |  | 2023-03-12
|  | ELECTRICALS |  | Not Yet Started |  |  | 2023-03-13
|  | CHLORINATOR |  | Not Yet Started |  |  | 2023-03-14
|  | GENSET |  | Not Yet Started |  |  | 2023-03-15
|  | SERVICE VEHICLE |  | Not Yet Started |  |  | 2023-03-16
|  | BRIDGE INTERCONNECTION |  | Not Yet Started |  |  | 2023-03-17
|  | OTHERS |  | Not Yet Started |  |  | 2023-03-18
GPM CALCULATOR | PUMP OPERATOR | GPM CALCULATOR | To record Pump GPM | Done
PUMP NON OPERATIONAL | PUMP OPERATOR | PUMP NON OPERATIONAL | To record the reason of Pump non operational hours | On-going |  |  | 2023-02-07
CRITICAL POINT MONITORING | PUMP OPERATOR | PSI READING | To record pressure from distribution | Done
DATA SYNCING | OS/CSA | DOWNLOAD DISPATCHED JO's |  | Not Yet Started | Waiting for Back-end |  | 2023-03-25
|  | UPLOAD ACCOMPLISHED JO's |  | Not Yet Started |  |  | 2023-03-26
|  | DOWNLOAD PUMP HOUSE ASSIGNMENT |  | Not Yet Started |  |  | 2023-03-27
|  | UPLOAD DAILY PUMP REPORT |  | Not Yet Started |  |  | 2023-03-28
|  | UPLOAD REPAIRS AND MAINTENANCE REPORT |  | Not Yet Started |  |  | 2023-03-29
|  | UPLOAD GPM HISTORY |  | Not Yet Started |  |  | 2023-03-30
|  | UPLOAD CRITICAL POINT MONITORING REPORT |  | Not Yet Started |  |  | 2023-03-31

## Detailed
Operations Mobile App |  |  | LEGENDS
Working Days (Timeline) |  |  |  |  | - | Not yet Started | [7 empty] | On Resume
[5 empty] | - | Started | [6 empty] | - | For Testing
Date Re-started: October 2022 |  |  |  |  | - | On-going | [6 empty] | - | Done
Estimated Date Finished: March 31, 2023 |  |  |  |  | - | Paused | [6 empty] | - | Sunday/Holiday
MODULE | DESCRIPTION | SUB-MODULE | TASK | OCTOBER | [30 empty] | NOVEMBER | [29 empty] | DECEMBER | [30 empty] | JANUARY | [30 empty] | FEBRUARY | [27 empty] | MARCH
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
PUMP PRODUCTION |  | ON/OFF RECORDS | UI/UX DESIGN | bar: OCTOBER 1
CODE | bar: OCTOBER 1
|  | FLOW METER READING | UI/UX DESIGN | bar: OCTOBER 1
CODE | bar: OCTOBER 1
|  | PRESSURE READING | UI/UX DESIGN | bar: OCTOBER 1
CODE | bar: OCTOBER 1
|  | CHLORINATOR DATA | UI/UX DESIGN | bar: OCTOBER 1
CODE | bar: OCTOBER 1
|  | PROBLEMS ENCOUNTERED | UI/UX DESIGN | bar: OCTOBER 1
CODE | bar: OCTOBER 1
JOB ORDERS |  | SERVICE APPLICATION SURVEY | UI/UX DESIGN | bar: OCTOBER 1
CODE | bar: OCTOBER 1
|  | NEW CONNECTION | UI/UX DESIGN | bar: OCTOBER 1
CODE | bar: OCTOBER 1
|  | METERING CONCERNS | UI/UX DESIGN
CODE
|  | CHANGE METER | UI/UX DESIGN
CODE
|  | DISCONNECTION - DELINQUENT ACCOUNT | UI/UX DESIGN
CODE
|  | DISCONNECTION - CUSTOMER REQUEST | UI/UX DESIGN
CODE
|  | RECONNECTION | UI/UX DESIGN
CODE
|  | SERVICE LEVEL | UI/UX DESIGN
CODE
|  | ILLEGAL CONNECTION | UI/UX DESIGN
CODE
|  | OTHERS | UI/UX DESIGN
CODE
PUMP REPAIRS AND MAINTENANCE |  | PUMP & MOTOR | UI/UX DESIGN
CODE
|  | CONTROL PANEL | UI/UX DESIGN
CODE
|  | PANEL BOARD | UI/UX DESIGN
CODE
|  | VFD | UI/UX DESIGN
CODE
|  | METER SET ASSEMBLY | UI/UX DESIGN
CODE
|  | FLOW METER | UI/UX DESIGN
CODE
|  | PRESSURE GAUGE | UI/UX DESIGN
CODE
|  | ELECTRICALS | UI/UX DESIGN
CODE
|  | CHLORINATOR | UI/UX DESIGN
CODE
|  | GENSET | UI/UX DESIGN
CODE
|  | SERVICE VEHICLE | UI/UX DESIGN
CODE
|  | BRIDGE INTERCONNECTION | UI/UX DESIGN
CODE
|  | OTHERS | UI/UX DESIGN
CODE
GPM CALCULATOR |  | GPM CALCULATOR | UI/UX DESIGN
CODE
PUMP NON OPERATIONAL |  | PUMP NON OPERATIONAL | UI/UX DESIGN
CODE
CRITICAL POINT MONITORI |  | PSI READING | UI/UX DESIGN
CODE
DATA SYNCING |  | DOWNLOAD DISPATCHED JO's | UI/UX DESIGN
CODE
|  | UPLOAD ACCOMPLISHED JO's | UI/UX DESIGN
CODE
|  | DOWNLOAD PUMP HOUSE ASSIGNMENT | UI/UX DESIGN
CODE
|  | UPLOAD DAILY PUMP REPORT | UI/UX DESIGN
CODE
|  | UPLOAD REPAIRS AND MAINTENANCE REPORT | UI/UX DESIGN
CODE
|  | UPLOAD GPM HISTORY | UI/UX DESIGN
CODE
|  | UPLOAD CRITICAL POINT MONITORING REPORT | UI/UX DESIGN
|  |  | CODE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31

## Sheet2
Service Application Survey | New Connection | Metering Concerns | Change Meter | Disconnection - Delinquent Account | Disconnection - Customer Request | Reconnection | Service Level | Illegal Connection | Others
Service Application Survey | New Connection | Metering Concerns | Change Meter | Disconnection - Delinquent Account | Disconnection - Customer Request | Reconnection | Service Level | Illegal Connection | Others